# Dival Intelligence Platform (DIP)

Execution Blueprint & Product Roadmap

Bilingual National Risk, Identity & Institutional Intelligence Platform
Version 1.0 · August 2026

| Initial Market Entry | Telecom Intelligence Exchange (TIX) |
| --- | --- |
| Initial Data | Existing institutional telecom debt datasets |
| Primary Languages | English and French |
| Long-Term Direction | Trusted cross-industry national intelligence infrastructure |

# 1. Executive Direction

DIP should be executed as a platform, not as a one-off telecom application. TIX is the first operational module because real telecom debt data is already available to drive the data model, ingestion pipeline, entity-resolution logic, and first customer workflows. The engineering strategy is therefore to prove the platform with telecom data, earn trust through governance and auditability, and only then expand to banks, insurers, utilities, enterprises, and authorized public institutions.

The first objective is not to build an African version of a mature credit bureau in one release. The first objective is to build a secure, bilingual, source-backed intelligence exchange that institutions can actually trust and use.

# 2. Product Scope

Universal business and individual search

Secure institutional data ingestion

Data validation and quality management

Canonical business/individual profiles

Entity resolution with confidence and human review

TIX telecom exposure and debt-aging intelligence

Portfolio monitoring and executive dashboards

Explainable risk indicators and versioned DIP risk assessments

Fraud/anomaly signals

Auditable reports and APIs

Grounded AI analyst capabilities

English/French experience across UI, reports and AI

# 3. Execution Principles

Real data first: Use the actual telecom datasets to define mappings and edge cases. Do not design the core schema around imagined perfect data.

Trust before AI: Provenance, permissions, data quality, audit and explainability come before predictive models.

Platform before industries: Build reusable identity, ingestion, search, audit and risk foundations. TIX is a module, not a separate codebase.

Human decision authority: DIP supports decisions; institutions retain final authority for credit, onboarding, service, collections and fraud actions.

Bilingual by design: English and French are architecture requirements, not a later translation project.

National trust must be earned: Position DIP as designed to become a trusted national reference; do not imply government endorsement or certification before it exists.

# 4. Target Architecture

Recommended MVP architecture:

Next.js/React + TypeScript web application

Single primary backend: FastAPI/Python or Spring Boot/Java

PostgreSQL canonical data store

S3-compatible object storage for immutable imports and reports

Redis for caching/jobs where needed

OIDC/OAuth2 identity with MFA

Queue/worker for imports, matching, reports and AI jobs

Infrastructure as Code and CI/CD

Central logs, metrics, traces and security audit events

PostgreSQL search initially; dedicated search engine when volume justifies it

# 5. Core Data Model

The most important architectural decision is to separate source records from canonical entities. A telecom row is evidence from a source; it is not automatically the definitive identity of a business or person.

| Layer | Purpose | Examples |
| --- | --- | --- |
| Source | Preserve exactly what an institution supplied | Import batch, raw row, source operator |
| Canonical Entity | Represent a resolved business or individual | Business, individual, identifiers, aliases |
| Relationship | Connect source evidence to entity | Match confidence, reviewed match |
| Exposure | Financial/account facts | Balance, aging, status, write-off |
| Intelligence | Derived decision support | Risk signals, score/rating, reason codes |
| Governance | Prove authorized use | Purpose, search log, audit, dispute |

# 6. Delivery Roadmap

| Phase | Timing | Primary Outcome |
| --- | --- | --- |
| Phase 0 — Discovery & Governance | Weeks 1–4 | Data inventory, legal/data-use review, source agreements, profiling, success metrics, threat model. |
| Phase 1 — Platform Foundation | Weeks 3–8 | Repo, environments, authentication/MFA, tenants, RBAC, bilingual framework, audit, base UI. |
| Phase 2 — Telecom Data Foundation | Weeks 6–12 | XLSX/CSV ingestion, mappings, immutable raw storage, validation, normalization, data-quality dashboard. |
| Phase 3 — Entity Resolution & Search | Weeks 10–16 | Canonical entities, identifiers, matching, confidence, review queue, universal search, profiles. |
| Phase 4 — TIX MVP | Weeks 14–20 | Telecom exposure, aging, cross-source views, repeat-default indicators, dashboards and reports. |
| Phase 5 — Risk Intelligence v1 | Weeks 18–24 | Transparent rules-based risk rating, reason codes, model registry, risk history, analyst review. |
| Phase 6 — Controlled Pilot | Weeks 22–30 | UAT, security/performance testing, training, governance review, KPI measurement. |
| Phase 7 — Multi-Telecom Production | Months 8–12 | Additional operators, automated feeds/APIs, alerts, disputes, SLA, DR, penetration test. |
| Phase 8 — Banking Expansion | Year 2 | Bank workflows, business credit intelligence, permitted individual risk, monitoring and APIs. |
| Phase 9 — Predictive AI | Year 2+ | Grounded AI analyst, recovery prediction, anomaly models, network analysis, explainable predictive risk. |

# 7. First 30 Days

## Week 1

Secure/inventory available datasets

Profile columns, missingness and duplicates

Document source/refresh process

Define data-handling rules and authorized purposes

## Week 2

Canonical data model

First telecom source mapping

Architecture skeleton

Repository/environments

Authentication and tenant model

## Week 3

Import pipeline

Validation engine

Immutable raw storage

Bilingual application shell

Audit logging

## Week 4

Normalized telecom records

First search API

Business profile

Data-quality dashboard

Demo with anonymized/approved records

# 8. 90-Day MVP Definition

At 90 days, the target is a secure bilingual MVP that can ingest the existing telecom dataset, validate it, preserve provenance, resolve entities, search businesses, show source-backed exposure and aging, and generate auditable intelligence reports. Individual search can be enabled only for fields and use cases that have been approved under the applicable governance and legal framework.

# 9. Risk Intelligence Strategy

Do not begin with an opaque machine-learning credit score. Start with a transparent rules-based risk assessment whose factors are visible and versioned. This produces a baseline that institutions can understand, challenge and validate. Predictive models should be introduced only after sufficient historical outcomes and governance exist.

Exposure

Debt aging

Payment/recovery behavior

Number of contributing sources

Repeat-default signals

Write-off/dispute status

Identity confidence

Fraud/anomaly indicators

Data recency

# 10. AI Roadmap

AI v1: Grounded summaries, data-quality explanations, natural-language portfolio queries, executive summaries.

AI v2: Collection prioritization and anomaly triage using validated platform features.

AI v3: Predictive recovery/risk models after historical outcomes are sufficient.

AI governance: Model registry, evaluation, reason codes, drift monitoring, rollback, human review and access-aware retrieval.

# 11. National Trust Framework

The strongest long-term differentiator is not the user interface. It is the trust network around the data. DIP should be engineered so that every important fact and decision-support output can be traced to its institutional source, every sensitive access can be audited, and every correction can preserve history.

Verified participating data sources

Clear participant data ownership

Purpose-based access

Data minimization

Tamper-resistant audit

Correction/dispute workflow

Independent security testing

Transparent risk methodology

Model governance

Regulator-ready documentation

# 12. Team & Workstreams

| Workstream | Responsibility |
| --- | --- |
| Product/Partnership | Requirements, telecom/bank relationships, pilot, commercial model |
| Data Engineering | Profiling, mappings, ingestion, quality, lineage |
| Backend | APIs, tenants, authorization, entity model, risk services |
| Frontend | Bilingual analyst and executive experience |
| Security/Governance | Threat model, privacy, access, audit, incident readiness |
| QA | Functional, security, data-quality, E2E and performance testing |
| AI/Analytics | Explainable rules first; grounded AI and predictive models later |
| DevOps | Environments, CI/CD, backups, observability, DR |

# 13. Pilot KPIs

Import success and rejection rate

Data completeness by source

Duplicate/entity-match precision

Median search response time

Percentage of displayed facts with complete provenance

Unauthorized-access test failures: zero

Analyst time saved per investigation

Number of useful cross-source matches

User adoption and repeat usage

Dispute/correction turnaround

Risk assessment reproducibility

System availability during pilot

# 14. Key Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Incomplete or inconsistent identifiers | Confidence-based entity resolution; never claim certainty; human review. |
| Data-use/legal uncertainty | Country-specific legal counsel and written source agreements before production sharing. |
| False matches | Conservative thresholds, source provenance, merge/unmerge, review queues. |
| Premature credit-score positioning | Start as explainable risk intelligence/decision support; formal scoring only with appropriate approvals. |
| Data breach | Encryption, MFA, least privilege, tenant isolation, audit, testing, incident response. |
| AI hallucination | Grounded retrieval, source-backed answers, no autonomous consequential decisions. |
| Partner concentration | Platform contracts, source onboarding model, reusable architecture, multi-institution roadmap. |
| Overbuilding | Ship TIX MVP first; defer advanced AI and cross-industry modules. |

# 15. Recommended Repository Structure

dip/
├── AGENTS.md
├── docs/
├── apps/
│   ├── web/
│   └── api/
├── workers/
│   ├── ingestion/
│   └── intelligence/
├── packages/
│   ├── ui/
│   ├── i18n/
│   └── shared/
├── infra/
├── scripts/
└── tests/

# 16. Immediate Build Order

1. Profile and document the real telecom spreadsheets.

2. Freeze v1 canonical data model and first source mapping.

3. Create repository, CI/CD and environments.

4. Implement identity, tenant, RBAC, MFA and audit foundations.

5. Implement bilingual UI/i18n foundation.

6. Implement immutable file ingestion and validation.

7. Implement normalization and data-quality review.

8. Implement business entity resolution and universal search.

9. Implement TIX exposure/aging profile and portfolio dashboard.

10. Implement reports and governed exports.

11. Implement explainable rules-based risk v1.

12. Run controlled pilot before predictive AI or bank expansion.

# 17. Deliverable Package

The accompanying engineering package contains:

PRODUCT_REQUIREMENTS.md

ARCHITECTURE.md

DATABASE_DESIGN.md

SECURITY_MODEL.md

API_STANDARDS.md

UI_DESIGN_SYSTEM.md

INTERNATIONALIZATION.md

DEVELOPMENT_RULES.md

TESTING_STRATEGY.md

DATA_GOVERNANCE.md

ROADMAP.md

AGENTS.md

Dival AI · Dival Intelligence Platform (DIP)